## Sheet1
Change Request Id | Date submitted | Submitted By | Description of change | Reason/Justification | Impact Analysis | Priority | Approval status | Approved by & date
1 | 2026-06-12 | Exam Controller | Online exam registration module for students | Reduce paper work,reduce queues,don't visit university as a inperson for registration | Core module,need database, login/signup page,registarion form UI. | High | Approved | Project Manager 13-June-2026
2 | 2026-06-11 | Project Manager | Need Admin Dashboard , Generate report for student grade,download excel format | Admin/exam controller needs report without any assistance of IT. | Admin Dashbard, export/download Bussiness logic | Medium | Approved | Project Manager 13-June-2026
3 | 2026-06-13 | Register | Student profille management and password reset functionality | Improve account security and allow students to manage their information indepently | User Profile Mangement, account settings, password reset and security features | High | Approved | Project Manager 13-June-2026
4 | 2026-06-14 | Exam Controller | Email notification system for register confirmation and result announcements | Ensure timely communication and reduce manual follow-up work | Notification System, email alerts and activity logs | Medium | Approved | Project Manager 13-June-2026